## Dashboard
Playwright SAP UI Automation – Project Tracker
Project Objective | Automate end-to-end creation/population of the control-plan workflow: download source workbook, read multiple sheets (CP Front Page and CP Grid), create parent/sub-child modules, assign data, add CP Grid rows, and validate results.
Planned Duration | 2–3 weeks
Automation Tool | Playwright + TypeScript/JavaScript
Source
Key Sheets | CP Front Page + CP Grid
UI Type | SAP-multi-step UI
Delivery Approach | Incremental: framework → data → UI → validation
Phase | Days
Analysis & Design | 2
Framework & Data | 3
Core UI Automation | 4
Validation & Error Handling | 2
Integration Testing | 2
Stabilization & Handover | 2
Key Assumption | Estimate assumes one automation engineer, stable test environment, required access available, and timely BA/SME clarification. Calendar delivery may shift if UI/business rules change.

## Detailed Plan
ID | Phase / Workstream | Activities | Deliverable / Exit Criteria | Estimate (Days) | Priority | Dependency | Status | Remarks
1 | Requirement Analysis & UI Mapping | Understand SAP-like navigation; identify parent/sub-child flow; map CP Front Page and CP Grid fields; confirm fixed cell mappings | Requirement + field mapping; navigation flow documented | 2 | High | BA / SME inputs | Not Started | Allow time for clarification of business rules
2 | Framework & Test Architecture | Define Page Objects, reusable utilities, locators, waits, logging, screenshots and test data structure | Reusable Playwright framework structure | 1 | High | Phase 1 | Not Started | Keep business data separate from UI code
3 | Excel Download & Parsing | Capture download; save workbook; read multiple sheets; extract fixed cells from CP Front Page and repeating rows from CP Grid | Reliable workbook reader returning typed data objects | 2 | High | Phase 1, 2 | Not Started | Handle missing/invalid cells and sheet names
4 | Parent & Sub-Child Creation | Automate creation of parent and two sub-child modules; navigate through nested screens | Modules created consistently from source data | 2 | High | Phase 1, 2 | Not Started | Complex UI navigation may require synchronization strategy
5 | Data Assignment & CP Grid Rows | Enter mapped front-page values; navigate into modules; add CP Grid rows and assign relevant data | End-to-end data population for representative scenario | 2 | High | Phase 3, 4 | Not Started | Validate row counts and key field values
6 | Validation & Exception Handling | Add assertions, field validation, duplicate handling, missing data handling, screenshots/logging | Clear pass/fail checks and diagnostics | 2 | High | Phase 5 | Not Started | Include negative/edge cases
7 | Integration Testing & Stabilization | Run full flow with multiple datasets; fix locator/timing/data issues; rerun regression | Stable end-to-end automation | 2 | High | Phase 6 | Not Started | Reserve capacity for UI changes
8 | Documentation & Handover | Test execution notes, configuration, assumptions, known limitations, run instructions | Handover-ready automation + documentation | 1 | Medium | Phase 7 | Not Started | BA/SME walkthrough

## Milestones
Milestone | Target | Acceptance Criteria | Owner | Status
M1 – Requirements & Mapping | End of Week 1 / Day 2 | UI flow and Excel-to-UI mapping agreed | Automation Engineer / BA | Not Started
M2 – Framework + Excel Reader | Day 5 | Download captured and all required sheets parsed | Automation Engineer | Not Started
M3 – Core Module Creation | Day 7 | Parent + 2 sub-child modules created reliably | Automation Engineer | Not Started
M4 – CP Grid Integration | Day 9 | CP Grid rows added and assigned to correct modules | Automation Engineer | Not Started
M5 – E2E Validation | Day 11 | Assertions, logging and exception handling working | Automation Engineer / SME | Not Started
M6 – Stable Demo Build | Day 13 | Representative datasets execute successfully | Automation Engineer | Not Started
M7 – Handover | Day 13–15 | Documentation + walkthrough complete | Automation Engineer / BA | Not Started

## Estimation
Workstream | Estimated Days | Low (Days) | High (Days) | Notes
Requirement analysis & UI mapping | 2 | 1.5 | 2.5 | Depends on BA/SME availability
Playwright framework / utilities | 1 | 1 | 1.5 | Page Objects, waits, logging
Excel download + multi-sheet parsing | 2 | 1.5 | 2.5 | CP Front Page + CP Grid
Parent/sub-child module creation | 2 | 2 | 3 | SAP-like nested navigation
Data assignment + CP Grid row creation | 2 | 2 | 3 | Main functional automation
Validation + exception handling | 2 | 1.5 | 2.5 | Assertions and diagnostics
Integration testing + stabilization | 2 | 2 | 3 | Multiple datasets
Documentation + handover | 1 | 0.5 | 1.5 | Runbook and walkthrough
TOTAL | 14 | 12 | 17 | ~2–2.5 calendar weeks depending on reviews/blockers

## Risks & Dependencies
ID | Risk / Dependency | Impact | Probability | Mitigation / Action | Owner | Status
R1 | SAP-like UI changes / unstable locators | High | Medium | Use resilient locators, Page Objects, centralized selectors; add synchronization utilities | Automation Engineer | Open
R2 | Business rules for parent/sub-child assignment unclear | High | Medium | Confirm mapping and expected hierarchy with BA/SME before coding | BA / SME | Open
R3 | Excel structure or sheet names change | Medium | Low | Validate workbook schema before processing; clear error messages | Automation Engineer | Open
R4 | Large CP Grid data volume affects execution time | Medium | Medium | Use reusable row-add methods; avoid unnecessary waits; validate counts | Automation Engineer | Open
R5 | Test environment / access issues | High | Medium | Confirm environment, credentials/access and test data early | Team | Open
R6 | Review / feedback delays | Medium | Medium | Provide incremental demo after core milestones rather than waiting for final delivery | Automation Engineer / BA | Open

## Technical Approach
Layer | Approach
Test Layer | End-to-end Playwright test orchestrating download → parse → UI creation → assignment → validation
Page Objects | Separate page classes for landing/navigation, parent module, sub-child/module details, and CP Grid screens
Excel Utility | Read workbook once; expose getFrontPageData() and getCPGridRows() methods; map fixed cells and repeating rows
Data Model | Convert workbook values into typed objects before UI interaction; avoid direct cell access in tests
Synchronization | Use Playwright locator-based waits and state-aware waits; avoid fixed sleeps wherever possible
Validation | Assert module hierarchy, key field values, CP Grid row count and critical row content
Diagnostics | Capture screenshot/trace/log on failure; include row/module context in errors
Maintainability | Centralize locators, field mappings, constants and reusable UI actions
Delivery Strategy | Build incrementally and demo after framework/data, module creation, and CP Grid integration milestones

## 3 Week Timeline
Day | Focus | Expected Output
1 | Requirement walkthrough + UI exploration | Confirmed workflow, screens, business rules
2 | Excel-to-UI mapping + technical design | Mapping and automation design signed off
3 | Playwright framework setup | Page Objects, utilities, logging skeleton
4 | Download handling + workbook parser | Reliable download and workbook access
5 | CP Front Page extraction + CP Grid model | Clean data objects ready for UI
6 | Parent creation automation | Parent module creation automated
7 | Sub-child creation automation | Two sub-child modules automated
8 | Navigation + assignment flow | Correct nested navigation and assignment
9 | CP Grid row insertion | Rows added to correct modules
10 | End-to-end integration | Full happy path running
11 | Assertions + exception handling | Functional validation and diagnostics
12 | Multiple dataset testing | Broader data coverage
13 | Bug fixing / stabilization | Stable demo build
14 | Regression + performance cleanup | Reliable reruns
15 | Documentation + BA walkthrough | Handover-ready build